## Form 6 -TFU
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
3rd QUARTER, CY 2022
Municipality of Kapalong
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Construction of NATIONAL HOUSING AUTHORITY (NHA 1) | BALAI TO ATA MANOBO TO KAMANSI, BRGY. GUPITAN | 15010000 | 2021-12-06 | 2022-09-01 | 99.91% | 14996239.91 |  | NHA
Construction of NATIONAL HOUSING AUTHORITY (NHA 2) | BALAI UG PAANAN TO MATIG TAPAYANON 1 BRGY. GUPITAN | 15010000 | 2021-12-06 | 2022-09-01 | 99.91% | 14996033.81 |  | NHA
Construction of NATIONAL HOUSING AUTHORITY (NHA 3 ) | BALAI UG PAANAN TO MATIG TAPAYANON 2, BRGY. GUPITAN | 15010000 | 2021-12-06 | 2022-09-01 | 99.91% | 14997033.8 |  | NHA
Construction of Multi Purpose Bldg. | MPB BRGY. MANIKI | 8000000 | 2022-05-17 |  |  |  | NO TRANSACTION YET | LGSF 2
IMPROVEMENT OF MABANTAO TO
CAPUNGAGAN FMR | FMI | 47353957.74 | 2022-06-15 | 2023-02-17 | 42.95% | 20340332.73 |  | DTI
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
MARY ELIZABETH L. EXALA |  | FREDESWINDA B. ESTRADA,CPA |  |  | MARIA THERESA R. TIMBOL
Local Budget Officer |  | Local Accountant |  |  | Local Chief Executive