## Form 7 - DFU
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: | REGION XI - DAVAO REGION |  | CALENDAR YEAR: | 2023
PROVINCE: | DAVAO DEL NORTE |  | QUARTER: | 2
CITY/MUNICIPALITY: | KAPALONG
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Social Development
Construction of Level II PWS | Purok 1, Florida | 1200000 |  |  |  | 737836.5 |  | Materials Delivered
Construction of Level II PWS | Purok 9 & Purok 11, Pag-asa | 2000000 |  |  |  | 1221290.75 |  | Materials Delivered
Installation of Solar Street Lights | Barangay Tiburcia | 1000000 | 2023-01-06 | 2023-10-08 | 100% | 895818.95 |  | For final Payment
Installation of Solar Street Lights | Purok 7,8,9 & 13 Sampao | 150000 | 6/26/2023 | 7/15/2023 | 100% | 120639.3 |  | For final Payment
Rural Electrification | Purok 7 to Purok 15 Sua-on | 2000000 | [5 empty] | POW Detailed Eng'g Design on Going
Installation of Solar Lights | Purok 9,10, & 11 Sua-on | 1000000 | [5 empty] | POW Detailed Eng'g Design on Going
Installation of Flood Lights | Purok 3, Sampao | 100000 | [5 empty] | POW Detailed Eng'g Design on Going
Construction of Multi-Purpose Building | Tiburcia | 1000000 | [5 empty] | For Savings
Construction of Multi-Purpose Building | Purok 1 Katipunan | 3000000 | [5 empty] | For Schedule of Bidding
Construction of Multi-Purpose Building | Barangay Katipunan | 2000000 | [5 empty] | For Savings
Construction of Multi-Purpose Building | Sitio Langan, Gupitan | 750000 | [5 empty] | POW Detailed Eng'g Design for Approval
Construction of Multi-Purpose Building | Sitio Upper Tagasan, Gupitan | 750000 | [5 empty] | POW Detailed Eng'g Design for Approval
Construction of Activity Center | Sitio Kapatagan, Gupitan | 2500000 | 4/13/2023 | 9/30/2023 | 44% |  |  | On Going / by Contract
Construction of Multi-Purpose Building | Barangay Mamacao | 2000000 | 2023-09-05 | 2023-09-09 | 32% |  |  | On Going / by Contract
Construction of Evacuation Center | Purok 6, Sampao | 2600000 | [5 empty] | For Bidding
Improvement of Multi-Purpose Building | Purok 12, Sampao | 100000 | [5 empty] | For Verification
Construction of Evacuation Center | Purok 1, Semong | 2000000 | [5 empty] | With Approved POW &
Improvement of Multi-Purpose Building | Purok 1, Gabuyan | 400000 | [5 empty] | Bidded
Improvement of Multi-Purpose Building | Purok 1, Gabuyan | 500000 | 2023-03-04 | 2023-10-06 | 81% | 480869.5 |  | On Going
Improvement of Evacuation Center | Purok 1, Gabuyan | 460000 | 2023-10-04 | 6/19/2023 | 91% | 452, 137.75 |  | On Going
| Total Social Development | 25510000 |  |  |  | 3908592.75
Economic Development
Site Development Project | Tomonas Area, Maniki | 2000000 | [5 empty] | With Approved POW
Urban Greening Projects- Phase III | Vicente Lim St. Maniki | 3116867 | [5 empty] | Bidded
Concreting of Barangay Roads | Purok 8 to Purok 10, Tiburcia | 2000000 | 2023-08-05 | 2023-03-08 | 90% | 1598813.45 |  | On Going
Concreting of Core Local Road | Purok 11D, Maniki | 5000000 | 2023-02-05 | 6/14/2023 | 100% | 4497401.91 |  | For Final Payment
Rehabilitation of Brgy. Roads | Sitio Wegi-Wegi to Mambato, Florida | 200000 | [5 empty] | To Start
Concreting of Barangay Roads | Purok 3, Mabantao | 2000000 | 2023-03-05 | 2023-01-08 | 90% |  |  | On Going / by Contract
Concreting of Core Local Road | Purok 3 to Purok 4, Luna | 2000000 | 2023-04-05 | 2023-02-08 | 90% | 1793882.72 |  | On Going
Construction of Drainage Canal | Purok 1, Tiburcia | 300000 | [5 empty] | On Going preparation of POW
Construction of Drainage Canal | Tiburcia Elementary School | 550000 | [5 empty] | On Going preparation of POW
Rehabilitation of Drainage System | Purok 10C, Maniki | 5000000 | [5 empty] | On Going preparation of POW
Installation of Culvert | Purok 7, Sampao | 50000 | [5 empty] | Pending for Verification
Concreting of Drainage Canal | Purok 2 & Purok 3, Florida | 1500000 |  |  |  | 933072.75 |  | Materials delivered
Declogging of Drainage System | Purok 10C, Maniki | 3500000 | [5 empty] | For Savings
Construction of Slope Protection | Purok 2, Sampao | 100000 |  |  |  | 55318 |  | Materials delivered
Construction of Multi-Purpose Pavement | Purok 10, Sampao | 200000 |  |  |  | 144150 |  | Materials delivered
Construction of Slope Protection | Gabions Purok 2, Sampao | 300000 |  |  |  | 198075 |  | Materials delivered
Construction of Multi-Purpose Pavement | Purok 2, Gabuyan | 340000 | [5 empty] | For Change of Location/ For Savings
Construction of Multi-Purpose Pavement | Purok 7, Gabuyan | 300000 |  |  |  | 184105.75 |  | Materials delivered
Construction of Wall Niches | Public Cemetery, Maniki | 1500000 | [5 empty] | On-going preparation of POW
Rehabilitation of Post Harvest Facility-Solar Dryer | Sitio Tagpopoot, Florida | 300000 |  |  |  | 35765.7 |  | Materials delivered
Rehabilitation of Post Harvest Facility-Solar Dryer | Purok 4, Florida | 300000 | 2023-01-05 | 5/31/2023 | 100% | 294979.7 |  | Completed
Rehabilitation of Post Harvest Facility-Solar Dryer | Sitio Wegi-Wegi, Florida | 300000 | 2023-01-06 | 5/15/2024 | 100% | 298169.5 |  | Completed
Rehabilitation of Post Harvest Facility-Solar Dryer | Sitio Camansi, Florida | 300000 | [5 empty] | Bidded
Rehabilitation of Post Harvest Facility-Solar Dryer | Sitio Upper, Florida | 300000 | 5/17/2023 | 6/20/2023 | 100% | 298129.58 |  | Completed
Rehabilitation of Post Harvest Facility-Solar Dryer | Sitio Tublihon, Florida | 300000 |  |  |  | 211814.7 |  | Materials delivered
Rehabilitation of Post Harvest Facility-Solar Dryer | Sitio Boholano, Florida | 300000 |  |  |  | 211814.7 |  | Materials delivered
Construction of Post Harvest Facility | Purok 6, Capungagan | 2000000 |  |  |  | 1356867.05 |  | Materials delivered
Maintenance of Barangay Roads |  | 4000000 | 1/27/2023 | 12/15/2023 | 78% | 3136702.89 |  | On Going
Maintenance of Municipal Roads |  | 1000000 | 2/28/2023 | 12/15/2023 | 75% | 750000 |  | On Going
Loan Amortization
- Principal | Heavy Equipment (Maniki) | 15669000 | 2/28/2018 | 2025-07-02 | 50% | 7834224.09
- Interest | Heavy Equipment (Maniki) | 2941000 |  |  |  | 882326.81
| Total Economic Development | 57666867 |  |  |  | 24715614.3
Environmental Management
N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Total Environmental Management | N/A
| Grand Total | 83176867 |  |  |  | 28624207.05
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
| Mary Elizabeth L. Exala |  |  |  | Maria Theresa R. Timbol
| Local Budget Officer |  |  |  | Local Chief Executive

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v2