## Form 7 - DFU
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: | REGION XI - DAVAO REGION |  | CALENDAR YEAR: | 2024
PROVINCE: | DAVAO DEL NORTE |  | QUARTER: | 2
CITY/MUNICIPALITY: | KAPALONG
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Social Development
Construction of Potable Water System | Purok 2, Sampao | 2000000 | [5 empty] | Deferred
Construction of Potable Water System | Purok 7 to Purok 8 brgy. Pag-asa | 2000000 | [5 empty] | For Savings
Construction of Potable Water System | Purok Camansi, Brgy Florida | 2000000 | [5 empty] | Schedule for Bidding
Construction of Potable Water System | Purok 5, Brgy. Gabuyan | 1500000 | 5/15/2024 | 7/31/2024 | 80% | 1208483.25 |  | On going
Purchase & Installation of Solar-Powered Outdoor lights for Barangay Tree Park |  | 200000 | [5 empty] | For PR
Installation of Solar Power Source | Mabuhay RCA, Brgy. Capungagan | 700000 | [5 empty] | For POW & Detailed Eng'g Design
Installation of Solar Street Lights | Purok 7 to Purok 9 Tiburcia | 1500000 | [5 empty] | For Savings
Construction of Multi-Purpose Building | Barangay Maniki | 5000000 | [5 empty] | For POW & Detailed Eng'g Design
Construction of Child Development Center | Sitio Lumad, Brgy. Gupitan | 1000000 | [5 empty] | Materials for Delivery
Construction of Child Development Center | Sitio Maguimon, Brgy Gupitan | 1000000 | [5 empty] | Materials for Bidding
Improvement of Adelanto Elementary School | Barangay Sua-on | 1000000 | 2024-01-06 | 7/30/2024 | 78.45% | 697087.96 |  | On going
Improvement of Sua-on Elementary School | Barangay Sua-on | 1000000 |  |  |  | 714539.15 |  | Materials Delivered
| Total Social Development | 18900000 |  |  |  | 2620110.36
Economic Development
Purchase of Land for Sanitary Landfill-add'l Fund | Tomonas Area, Maniki | 1700000 | [5 empty] | Not yet Implemented
Purchase of Lot for Barangay Hall Capungagan | Barangay Capungagan | 2000000 | [5 empty] | Not yet Implemented
Site Development for Barangay Tree Park |  | 500000 | [5 empty] | For POW & Detailed Eng'g Design
Urban Greening Projects | Vicente Lim St., Maniki | 4000000 | [5 empty] | Materials Delivered
Concreting of Barangay Roads | Purok 4 to Purok 4A Semong | 2000000 | [5 empty] | For Savings
Concreting of Barangay Roads | Purok 3 to Purok 4 Mabantao | 2000000 | [5 empty] | For Savings
Concreting of Core Local Road | Villa Clementa, Maniki | 8310892 | [5 empty] | Bidded
Concreting of Barangay Roads | Purok 6, Luna | 2000000 | [5 empty] | For Savings (Change Location)
Construction of Drainage Canal | Villa Clementa, Maniki | 3000000 | [5 empty] | Bidded and Awarded
Construction of Drainage System | Purok 1 to Pk1A Brgy. Katipunan | 2000000 | [5 empty] | Bidded
Declogging of Drainage System | Barangay Maniki | 5000000 | 2024-02-01 | 12/31/2024 | 22% | 1146825 |  | On Going
Improvement of Public Cemetery | Barangay Maniki | 1300000 | 2024-11-04 | 7/31/2024 | 100% | 1296554.65 |  | Completed
FITS Service Center Enhancement |  | 550000 | [5 empty] | For POW & Detailed Eng'g Design
Improvement of Post-Harvest Facility | Purok 2 Brgy Gabuyan | 500000 | [5 empty] | Materials for Delivery
Construction of Activity Centers | Barangay Mamacao | 2000000 | [5 empty] | CAFOA on Process
Construction of Waiting Shed | Adelanto Elem. School, Brgy Sua-on | 500000 | [5 empty] | For Savings
Purchase of 2 units Dumptrucks |  | 10000000 | [5 empty] | Not yet Implemented
Maintenace of Brgy Roads |  | 4000000 | 1/25/2024 | 12/31/2024 | 66% | 2663529 |  | On Going
Maintenance of Municipal Roads |  | 1000000 | 1/25/2024 | 12/31/2024 | 75% | 750000 |  | On Going
Loan Amortization
- Principal | Heavy Equipment (Maniki) | 15669000 | 2018-08-02 | 2025-07-02 | 50% | 7834224.08 |  | On going
- Interest | Heavy Equipment (Maniki) | 1374000 |  |  |  | 625879.36 |  | On going
| Total Economic Development | 69403892 |  |  |  | 14317012.09
Environmental Management
N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Total Environmental Management | N/A
| Grand Total | 88303892 |  |  |  | 16937122.45
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
| Mary Elizabeth L. Exala |  |  |  | Maria Theresa R. Timbol
| Local Budget Officer |  |  |  | Local Chief Executive

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v2